## Sheet1
| WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5
| 15. | 16. | 17. | 18. | 19. | 20. | 21. | 22. | 23. | 24. | 25. | 26. | 27. | 28. | 29. | 30. | 01. | 02. | 03. | 04. | 05. | 06. | 07. | 08. | 09. | 10. | 11. | 12. | 13. | 14. | 15. | 16. | 17. | 18. | 19.
| Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
PROJECT PLANNING
Gantt chart | bar: WEEK 1 15. Mon. to WEEK 1 16. Tue.
Kanban board | bar: WEEK 1 15. Mon. to WEEK 1 16. Tue.
DESIGN
Styleguide | bar: WEEK 1 17. Wed. to WEEK 1 18. Thur.
Project prototype | bar: WEEK 1 17. Wed. to WEEK 1 21. Sun.
PRE PROGRAMMING
Open new repo | bar: WEEK 2 22. Mon. to WEEK 2 23. Tue.
Add dependencies | bar: WEEK 2 22. Mon. to WEEK 2 23. Tue.
Add testcommands | bar: WEEK 2 24. Wed. to WEEK 2 25. Thur.
Add workflows | bar: WEEK 2 24. Wed. to WEEK 2 25. Thur.
Deploy with workflow | bar: WEEK 2 24. Wed. to WEEK 2 25. Thur.
PROGRAMMING(start with testscases)
Landingpage/Public feed | bar: WEEK 2 25. Thur. to WEEK 2 27. Sat.
Search funcitonality | bar: WEEK 2 27. Sat. to WEEK 2 28. Sun.
Login functionality | bar: WEEK 3 29. Mon. to WEEK 3 01. Wed.
Register functionality | bar: WEEK 3 01. Wed. to WEEK 3 03. Fri.
Logout functionality | bar: WEEK 3 03. Fri.
Profile page | bar: WEEK 3 04. Sat. to WEEK 3 05. Sun.
Logged in feed | bar: WEEK 4 06. Mon.
Create new listing functionality | bar: WEEK 4 07. Tue. to WEEK 4 09. Thur.
Bidding functionality | bar: WEEK 4 09. Thur. to WEEK 4 11. Sat.
View bids functionality | bar: WEEK 4 11. Sat. to WEEK 4 12. Sun.
DELIVERY
Hand in for feedback | bar: WEEK 4 12. Sun.
Adjust according to feedback | bar: WEEK 5 13. Mon. to WEEK 5 15. Wed.
Hand in all links | bar: WEEK 5 16. Thur. to WEEK 5 19. Sun.